## UI vs WBS — Detail
Deuxième Souffle — UI vs WBS Mismatch Analysis (APA Coach)
Story ID | Screen / Feature | Field / Element | WBS Spec (AC / Story) | UI Actual (Video) | Status
Authentication & Registration
AUTH-01 | Registration — Step 1 (Coach Identity) | Date of birth field | WBS: Date of birth field | Date of birth NOT visible in registration form | MISSING
AUTH-02 | Login | Google OAuth button | WBS: Coach can log in via Google OAuth | Google OAuth button NOT on login screen | MISSING
AUTH-19 | Pending Approval Screen | Document status per item | WBS: Visual status for each doc — CV (received/pending), URSSAF, insurance, etc. | Screen shows doc list with 'To add' buttons but no received/pending status per doc | MISMATCH
AUTH-19 | Pending Approval Screen | Indicative processing time | WBS: Indicative processing time displayed | NOT shown on pending screen | MISSING
Dashboard / Home
PLA-01 | Dashboard — Home | Coach badge | WBS: Dashboard displays Coach badge | No badge shown | MISSING
PLA-01 | Dashboard — Home | Session card: Unit type | WBS: Session cards display Unit type | Unit type NOT shown on next-session card | MISSING
Profile & Availability
PLA-08 | Profile — Availability | Transport mode options | WBS: Car / Two-wheel vehicle options | UI shows: Car, Walking, Other — 'Two-wheel vehicle' replaced by 'Walking' and 'Other' | MISMATCH
PLA-08 | Profile — Availability | Max travel time slider | WBS: Slider 10–90 minutes range | UI shows discrete options: ≤15, ≤30, ≤45, ≤60 min (no slider, max 60 not 90) | MISMATCH
PLA-08 | Profile — Availability | Multiple departure addresses | WBS: Coach can update a primary departure address (+ secondary implied by 'Departure addresses' plural in spec overview) | UI shows single 'Departure address' field | MISMATCH
PLA-09 | Profile — Availability | Availability | WBS: The coach can activate or deactivate availability for each half-day. | UI only shows weekday only
Assigned session
PLA-14 | Session Detail — Confirmed | Coach hourly rate | WBS: Screen displays Coach hourly rate | Hourly rate NOT shown in session detail sheet | MISSING
PLA-14 | Session Detail — Confirmed | Action: Late | WBS: Coach can declare a delay by selecting 'Late' | 'Declare absence' shown in Manage section — 'Late' action missing | MISSING
Cancellation Flow
PLA-11 | Absence Declaration | Absence Declaration form | WBS: a 3 step required form | Simple confirmation in 1 step | MISMATCH
Available Sessions
PLA-04 | Available — Weekly View | Sessions grouped by day with count | WBS: System groups available sessions by day, displays count per day | Calendar dots shown per day but no explicit count per day label | MISMATCH
Sessions List (Confirmed / Past)
PLA-06 | Available — Session Detail | Travel time warning if exceeds coach max | WBS: Warning if estimated travel time exceeds coach's maximum | No warning shown even for Greenfield Lodge at 15.4 km (well over 45 min max) | MISSING
PLA-06 | Available — Session Detail | Access instructions field | WBS: Session context (first visit, etc.) | 'Access: Main entrance, 14 Quai Rambaud' shown — extra detail beyond WBS spec | EXTRA
PLA-02 | Sessions — Confirmed tab | 'Copy address' button in session detail | WBS: EHPAD address copyable via 'Copy address' button (no Google Maps API) | No copy address option in confirmed session detail — only Directions + Check in | MISSING
PLA-02 | Sessions — Confirmed tab | Option to switch to monthly view | WBS: Assigned session is displayed in list/week/month view | Weekly / June (monthly) tabs present on Home; Sessions screen is list-only with no view of weekly/monthly | MISMATCH
Post-Session Report
SESS-01 | Post-Session Report | Overall participant engagement (4 emoji options) | WBS: 😴 Rather tired / 😐 Average / 🙂 Well engaged / 🔥 Very dynamic | Report uses '6 — Session atmosphere' with ★ star rating + emoji label (e.g. 🔥 On fire) | MISMATCH
SESS-01 | Post-Session Report | Session difficulty field (Easy / Standard / Demanding) | WBS: Coach selects perceived session difficulty | Difficulty field NOT present in report | MISSING
SESS-01 | Post-Session Report | Activities covered (multi-select) | WBS: Not in WBS spec — not listed as a field | '2 — Activities covered' multi-select (Mobility & balance, Strength, Flexibility, Coordination, Cardio, Cognitive games) shown | EXTRA
SESS-01 | Post-Session Report | 'Was the facility ready for you?' (Yes/No) | WBS: Not in WBS spec | '5 — Was the facility ready for you?' shown | EXTRA
PLA-07 | Sessions — Applications tab | Application statuses: Pending / Accepted / Declined | WBS: After withdrawing → removed from candidate list. Accepted/declined not specified as states | UI shows Pending, Accepted, Declined statuses + date and location per application | EXTRA
SESS-05 | [Not shown] | Report history list | WBS: Chronological list of submitted reports, filter by date/facility, pagination | Not demonstrated in video | MISSING
SESS-06 | [Not shown] | EHPAD feedback / rating detail screen | WBS: Coach views EHPAD feedback per session — EHPAD name, date, rating, comment | Not demonstrated in video | MISSING
Gamification
GAME-01 | [Not shown] | Coach Badges system | WBS GAME-01: Badge system | Not implemented / not shown | MISSING
GAME-02 | [Not shown] | Coach Levels & Progression | WBS GAME-02: Levels & progression | Not implemented / not shown | MISSING
AUTH-14 | [Not shown] | Delete account request | WBS: Coach can submit deletion request | Not present in Profile / Account section | MISSING